RISK MANAGEMENT Software Engineering — Complete Study Notes Based on Pressman's Software Engineering: A Practitioner's Approach, 7/e

COLOR CODING GUIDE 🔵 Blue boxes — Core theory notes & key concepts 🟢 Green boxes — Scenario-based exam questions with model answers 🟠 Orange boxes — Short questions (likely exam questions) 🟣 Purple table — Key terminology reference ⬜ Grey rows — Risk attribute tables

SECTION 1: CORE CONCEPTS

## 1.1 What is a Project Risk?

Four key questions define any risk: - ISSUE — What can go wrong? - PROBABILITY OF OCCURRENCE — How likely is it? - IMPACT — What damage will it cause? - MITIGATION — What can we do about it?

## 1.2 Reactive vs. Proactive Risk Management

| Reactive (Fire-Fighting) | Project team reacts only when a risk occurs. Strategies: Fix-on-Failure (apply resources when risk strikes) or Crisis Management (recover after project failure). |
| --- | --- |
| Proactive (Preventive) | Formal risk analysis is performed in advance. Organization corrects root causes, examines external risk sources, and develops change management skills. |
| Mitigation (Reactive) | Plan for additional resources in anticipation of the risk, before it becomes a crisis. |
| Crisis Management | Recovery strategy if a project-failure event actually occurs. |

## 1.3 The 7 Principles to Avoid Project Failure

1. Maintain a global perspective: Identify all software risks within the full scope of the application system. 2. Take a forward-looking view: Establish a Plan B for every significant risk before it materialises. 3. Encourage open communication: Never dismiss a potential risk raised by any team member. 4. Integrate risk management: Embed risk consideration into every stage of software development. 5. Emphasise a continuous process: Teams must continuously monitor evolving risks and update mitigation plans. 6. Develop a shared product vision: When all stakeholders share the same scope, risk assessment becomes more accurate and consistent. 7. Encourage teamwork: Pool the talents, skills, and knowledge of every stakeholder.

SECTION 2: RISK IDENTIFICATION CATEGORIES

## Seven Risk Categories

▶ Product Size

Risks from the overall size of software being built or modified. Key Attributes: - Size in LOC/FP, number of programs, files, or transactions - % deviation from average past products - Size of database - Number of users - Number of changes before & after delivery - Amount of reused software

▶ Business Impact

Risks from management constraints and marketplace forces. Key Attributes: - Effect on company revenue - Reasonableness of delivery deadlines - Interoperability constraints - Sophistication of end users - Government/regulatory constraints - Cost with late delivery - Cost with a defective product

▶ Customer Characteristics

Risks from poor customer knowledge or communication failures. Key Attributes: - Does customer know requirements well? - Is customer willing to dedicate time to the technical team? - Is customer participating in reviews? - Is customer technically sound? - Does customer understand SE practices?

▶ Process Maturity

Risks from the defined software process followed by the organisation. Key Attributes: - Is a process framework established? - Are teams following the process? - Is there management support for SE practices? - Is there a proactive SQA approach? - Are technical reviews conducted? - Are documentation formats established?

▶ Development Environment

Risks from availability and quality of development tools. Key Attributes: - (Assessed via tool availability, integration, and team familiarity with toolchain)

▶ Technology to be Built

Risks from complexity and novelty of the system. Key Attributes: - Is the technology new to the organisation? - Are new algorithms or I/O techniques used? - New or improved hardware? - Specialised UI requirements? - Is the application radically different from past work? - Significant performance constraints? - Is the required functionality doubtfully achievable?

▶ Staff Size & Experience

Risks from the technical and project experience of software engineers. Key Attributes: - Are the best people available? - Do staff have the right skill set? - Is the team large enough? - Is the workforce committed and dedicated? - Has necessary training been received? - Will staff turnover be low?

SECTION 3: RISK ASSESSMENT & ESTIMATION

## 3.1 Risk Components

| Performance Risk | Uncertainty that the product will meet its requirements and be fit for intended use. |
| --- | --- |
| Cost Risk | Uncertainty that the project budget will be maintained. |
| Support Risk | Uncertainty that the software will be easy to correct, adapt, and enhance. |
| Schedule Risk | Uncertainty that the project schedule will be maintained and the product delivered on time. |

## 3.2 Risk Estimation

Each risk is rated on two dimensions: 1. Probability — The likelihood that the risk is real (0–1 or %). 2. Consequence/Impact — The severity of problems if the risk occurs (scale 1–5, where 1 = low and 5 = catastrophic).

## 3.3 Risk Exposure (RE) Formula

RE = P × C P = Probability of occurrence for the risk C = Cost to the project if the risk occurs 📌 Worked Example: • Only 70% of planned reusable components (60 total) will integrate → 18 must be custom-built. • P = 0.80 (80% likely) • C = 18 components × 100 LOC × $14/LOC = $25,200 • RE = 0.80 × $25,200 ≈ $20,200

## 3.4 Project Risk Assessment Checklist

Key assessment questions (answer YES = lower risk, NO = higher risk): - Have top software and customer managers formally committed to support the project? - Are end-users enthusiastically committed to the project? - Are requirements fully understood by the SE team and customers? - Have customers been fully involved in requirements definition? - Do end-users have realistic expectations? - Is project scope stable? - Does the SE team have the right mix of skills? - Are project requirements stable? - Does the team have experience with the technology to be implemented? - Is the team size adequate for the job? - Do all customer/user constituencies agree on project requirements?

## 3.5 Risk Mitigation, Monitoring & Management (MMM)

| Mitigation | How can we AVOID the risk? Proactive steps to reduce probability or impact. |
| --- | --- |
| Monitoring | What factors can we TRACK to see if the risk is becoming more or less likely? |
| Management | What CONTINGENCY PLANS exist if the risk becomes reality? |

SECTION 4: KEY TERMINOLOGY REFERENCE

| Term | Definition |
| --- | --- |
| Risk | An uncertain event or condition that, if it occurs, has a positive or negative effect on a project. |
| Risk Exposure (RE) | RE = P × C; the combined measure of probability and cost impact of a risk. |
| Mitigation | Proactive steps taken to reduce the likelihood or impact of a risk. |
| Monitoring | Ongoing tracking of risk indicators to detect if a risk is increasing or decreasing. |
| Contingency Plan | A pre-defined response plan activated when a risk actually materialises. |
| Crisis Management | Recovery activities undertaken after a project-failure event has occurred. |
| Fix-on-Failure | Reactive strategy: resources are applied only when the risk actually strikes. |
| Performance Risk | Uncertainty that the product will meet specified requirements. |
| Cost Risk | Uncertainty that the project will remain within budget. |
| Schedule Risk | Uncertainty that the project will be delivered on time. |
| Support Risk | Uncertainty that the delivered software will be maintainable and adaptable. |
| Proactive RM | Formal upfront risk analysis; organisation corrects root causes before problems occur. |
| Reactive RM | Risk management that happens only after a risk event has occurred. |
| LOC | Lines of Code — a size metric used to estimate project effort and risk. |
| FP | Function Points — an alternative size metric, independent of programming language. |

SECTION 5: SCENARIO-BASED EXAM QUESTIONS

These scenario questions test deep understanding. Practice writing full answers.

🔷 SCENARIO 1 Your team is developing an e-commerce platform. During planning, a developer mentions that 30% of the reusable components from the last project might not integrate with the new framework. The project manager dismisses this concern to keep the meeting short. ❓ Question: Which of the 7 principles did the project manager violate, and what should they have done instead? ✅ Model Answer: The manager violated Principle 3 (Encourage Open Communication) — potential risks should never be dismissed. The manager should have logged the concern, assigned a team member to investigate integration compatibility, estimated the probability and cost impact (using RE = P × C), and included a mitigation plan in the risk register.

🔷 SCENARIO 2 A government agency contracts a software firm to build a tax-processing system. The agency representative rarely attends review meetings and struggles to clearly define the final requirements. The SE team proceeds with assumptions. ❓ Question: Identify the risk category and explain the likely consequences. ✅ Model Answer: This is a Customer Characteristics risk. Because the customer lacks knowledge and is unavailable for timely communication, requirements may be misunderstood. Consequences include rework after delivery, schedule slippage, and budget overruns. The team should implement formal sign-off sessions and prototype-based requirement walkthroughs to engage the customer.

🔷 SCENARIO 3 A startup decides to build an AI-powered medical diagnosis tool using a deep learning framework none of the developers have used before. The tool must also meet FDA regulatory requirements. Delivery is in 6 months. ❓ Question: Perform a risk identification for this scenario, naming at least three risk categories and one attribute each. ✅ Model Answer: ① Technology Risk — The deep learning framework is new to the organisation; novel algorithms increase uncertainty. ② Staff Risk — No one on the team has experience with this technology stack, raising failure probability. ③ Business Impact Risk — Government (FDA) constraints add compliance overhead and potential legal penalties for late/defective delivery. Mitigation: prototype sprint with the new framework, regulatory consultant, and revised schedule.

🔷 SCENARIO 4 During a mid-project risk review, the team discovers that their database size has grown 4× beyond original estimates and the number of concurrent users has tripled due to unexpected market adoption. ❓ Question: Using the RE formula, explain how the project's risk exposure has changed and what monitoring steps should be taken. ✅ Model Answer: Product Size risk has escalated sharply. The original RE = P × C must be recalculated: if the probability of performance degradation rises from 20% to 60% and estimated cost of failure doubles, RE quadruples. Monitoring steps: track query response times, server load, and rollback frequency as early warning indicators. Mitigation: database partitioning, load testing, and infrastructure scaling plan.

🔷 SCENARIO 5 A software company consistently reacts to project failures rather than preventing them. After three failed projects, the CEO mandates a shift to formal risk management. ❓ Question: Compare the reactive and proactive risk management paradigms and explain the key changes the company must implement. ✅ Model Answer: Reactive RM (current state): risks are addressed only after they occur via fix-on-failure or crisis management — expensive and disruptive. Proactive RM: formal risk analysis is conducted at project start; root causes are identified; the organisation builds risk management skills and monitors external risk sources continuously. Required changes: establish a risk register, perform RE scoring at each sprint, assign risk owners, and mandate mitigation plans for all high-RE items before development begins.

🔷 SCENARIO 6 Two developers disagree about whether a 'schedule risk' or a 'cost risk' is more dangerous for their current project. The project is a fixed-price contract with a penalty clause for late delivery. ❓ Question: Define both risk components and argue which poses greater RE in this specific context. ✅ Model Answer: Schedule Risk is uncertainty that the project will not be delivered on time. Cost Risk is uncertainty that the budget will be exceeded. In a fixed-price, penalty-clause contract, Schedule Risk has the higher RE: late delivery directly triggers financial penalties (raising C), and schedule slippage is already more probable given fixed-price pressure on scope. However, both compound each other — delays cause overtime costs, merging both risks.

SECTION 6: SHORT EXAM QUESTIONS

These short questions are likely to appear directly on exams. Learn these answers precisely.

Q1. What is a project risk? A: A project risk is an uncertain event characterised by: what could go wrong (Issue), how likely it is (Probability), what damage it causes (Impact), and what can be done (Mitigation).

Q2. Differentiate between reactive and proactive risk management. A: Reactive RM reacts to risks after they occur (fix-on-failure or crisis management). Proactive RM performs formal risk analysis upfront, identifies root causes, and builds mitigation plans before problems arise.

Q3. What is the Risk Exposure (RE) formula? A: RE = P × C, where P = probability of risk occurrence and C = cost to the project if the risk occurs.

Q4. List the four risk components. A: Performance Risk, Cost Risk, Schedule Risk, and Support Risk.

Q5. Name any four of the seven principles to avoid project failure. A: Any four from: Global perspective, Forward-looking view, Open communication, Integration of risk, Continuous monitoring, Shared product vision, Teamwork.

Q6. What are the three elements of Risk MMM? A: Mitigation (avoid/reduce the risk), Monitoring (track indicators), Management (contingency planning if risk occurs).

Q7. List the seven risk categories in software engineering. A: Product Size, Business Impact, Customer Characteristics, Process Definition/Maturity, Development Environment, Technology to be Built, Staff Size and Experience.

Q8. What is 'fix-on-failure'? A: A reactive risk strategy where resources are located and applied only after a risk event strikes the project.

Q9. How is impact rated in a risk table? A: On a scale of 1–5: 1 = low impact on project success, 5 = catastrophic impact on project success.

Q10. What is staff/people risk? A: Risks associated with the availability, skill set, experience, commitment, training, and turnover of the software engineering team.

Q11. Why is 'customer characteristics' a risk factor? A: Because uninformed or unavailable customers can cause poor requirement definition, leading to rework, delays, and budget overruns.

Q12. What does 'process maturity risk' assess? A: Whether the development organisation has an established, followed, and management-supported software process framework, including SQA and technical reviews.

Q13. Calculate RE: P = 0.5, C = $10,000. A: RE = 0.5 × $10,000 = $5,000.

Q14. What is technology risk? A: Risk associated with the complexity and novelty of the system to be built — new algorithms, hardware, UI requirements, or SE methods.

Q15. In the shared product vision principle, what is the benefit? A: When all product owners share the same scope, risk assessment is more accurate and everyone remains aligned, reducing miscommunication risks.

Q16. What is support risk? A: The degree of uncertainty that the delivered software will be easy to correct, adapt, and enhance after release.

Q17. Define 'crisis management' in the context of risk. A: A recovery strategy activated if a project encounters an event that leads to, or threatens, project failure — the most extreme form of reactive risk management.

Q18. What attributes indicate product size risk? A: LOC/FP estimates, % deviation from past products, database size, number of users, number of changes, and amount of reused software.

SECTION 7: SOLVED RE = P × C CALCULATION SCENARIOS

Each scenario below walks through the complete Risk Exposure calculation. Study the working carefully — examiners love numerical RE problems.

RE = P × C P = Probability (0.0 – 1.0) ¦ C = Cost if risk occurs ($) ¦ RE = Risk Exposure ($)

📊 RE SCENARIO 1: Reusable Components (Pressman's Classic Example) Given: A project plans to reuse 60 software components. Only 70% are expected to integrate successfully. Average component = 100 LOC. Development cost = $14/LOC. Probability = 80%. Step-by-Step Working: - Components that CANNOT be reused = 60 × (1 – 0.70) = 60 × 0.30 = 18 components - Cost to develop 18 components from scratch = 18 × 100 LOC × $14/LOC = $25,200 - P = 0.80 (80% likelihood that this risk is real) - C = $25,200 (cost if risk occurs) - RE = P × C = 0.80 × $25,200 = $20,160 ✅ Result: RE ≈ $20,160 💡 Insight: Even though the risk is not certain, the organization must budget ~$20K as contingency. This risk is HIGH priority because both P and C are large.

📊 RE SCENARIO 2: Hardware Delivery Delay — Schedule Risk Given: Embedded software for XYZ system. Tests depend on a hardware component under development. Hardware delivery may be delayed. Probability = 60%. Each day of delay costs $1,500 in idle developer time. Expected delay = 20 days if risk occurs. Step-by-Step Working: - Cost of delay = 20 days × $1,500/day = $30,000 - P = 0.60 (60% probability hardware is delayed) - C = $30,000 (cost if risk occurs) - RE = P × C = 0.60 × $30,000 = $18,000 - Additionally: 6 person-months of extra resource are estimated, so if avg monthly cost = $5,000 → extra C = $30,000 (can be used as alternate C) ✅ Result: RE = $18,000 (or up to $18,000–$36,000 range depending on cost basis) 💡 Insight: This is a Schedule Risk with Priority 4 (high). Since P=0.60 is above the typical 0.50 threshold, this risk is considered LIKELY and must be actively monitored via milestone reviews with the hardware group.

📊 RE SCENARIO 3: Staff Turnover — People Risk Given: 3 key engineers on a 12-month project may leave mid-project. Probability of at least one departure = 40%. Cost to recruit, onboard, and ramp up a replacement = $20,000 per person. Assume 1.5 staff lost on average if risk occurs. Step-by-Step Working: - Average number of staff lost if risk occurs = 1.5 engineers - Cost per lost engineer = $20,000 - C = 1.5 × $20,000 = $30,000 - P = 0.40 - RE = P × C = 0.40 × $30,000 = $12,000 ✅ Result: RE = $12,000 💡 Insight: Staff/People risk is often underestimated. Even at only 40% probability, a $12K exposure justifies retention bonuses, knowledge documentation, and cross-training to mitigate.

📊 RE SCENARIO 4: Requirements Instability — Schedule + Cost Risk Given: Customer has been changing requirements frequently. Probability that requirements will change significantly after design phase = 70%. Cost of rework per major change = $8,000. Historical data shows an average of 3 major changes occur if instability hits. Step-by-Step Working: - Expected rework cost if risk occurs = 3 changes × $8,000 = $24,000 - P = 0.70 (high probability — customer is known to be unstable) - C = $24,000 - RE = P × C = 0.70 × $24,000 = $16,800 ✅ Result: RE = $16,800 💡 Insight: This is a Customer Characteristics risk. With P=0.70 it is almost certain to occur. Mitigation: freeze requirements with formal sign-off after design phase, use Change Control Board for any modifications.

📊 RE SCENARIO 5: Comparing Two Risks — Which Has Higher Priority? Given: Risk A: Database performance failure. P = 0.30, C = $50,000. Risk B: Third-party API discontinuation. P = 0.80, C = $10,000. Which risk should be prioritized? Step-by-Step Working: - RE(A) = P × C = 0.30 × $50,000 = $15,000 - RE(B) = P × C = 0.80 × $10,000 = $8,000 - Compare: RE(A) = $15,000 > RE(B) = $8,000 - Risk A has higher exposure despite lower probability — the catastrophic cost outweighs the lower likelihood - Sort risk table: Risk A ranked above Risk B ✅ Result: Risk A (RE=$15,000) has higher priority than Risk B (RE=$8,000) 💡 Insight: This is why you CANNOT prioritize risks by probability alone. RE = P × C captures both dimensions. A low-probability, high-impact risk can outrank a high-probability, low-impact one.

📊 RE SCENARIO 6: Process Immaturity — Cost Risk Given: A company with no formal SQA process is taking on a safety-critical project. Probability that lack of process leads to major defects requiring post-delivery rework = 65%. Estimated cost of post-delivery fixes + client penalties = $45,000. Step-by-Step Working: - P = 0.65 - C = $45,000 - RE = P × C = 0.65 × $45,000 = $29,250 - This is the HIGHEST RE in any reasonable risk table for this project - Impact rating on 1–5 scale = 5 (catastrophic) — safety-critical failure ✅ Result: RE = $29,250 — CRITICAL PRIORITY 💡 Insight: Process Maturity Risk with catastrophic impact must trigger immediate mitigation: adopt a lightweight process framework, institute mandatory code reviews, and engage an external SQA consultant before development begins.

SECTION 8: RECORDING RISK INFORMATION — SCENARIO PRACTICE

Risk Information Record Format Each risk should be formally documented using the following fields (as shown in the Pressman template): - Project — Name of the project - Risk Type — Category of risk (schedule, cost, performance, support, etc.) - Priority (1–5) — 1 = low, 5 = critical - Risk Factor — Description of what could go wrong - Probability — Likelihood expressed as a percentage - Impact — Description of the consequence if risk occurs - Monitoring Approach — How will this risk be tracked? - Contingency Plan — What will we do if it occurs? - Estimated Resources — Additional resources needed if risk materialises

▶ Risk Record 1: Hardware Delivery Delay (from Pressman's Example)

| Project | Embedded software for XYZ system |
| --- | --- |
| Risk Type | Schedule Risk |
| Priority (1 low … 5 critical) | 4 |
| Risk Factor | Project completion will depend on tests which require a hardware component under development. Hardware component delivery may be delayed. |
| Probability | 60% |
| Impact | Project completion will be delayed for each day that hardware is unavailable for use in software testing. |
| Monitoring Approach | Scheduled milestone reviews with hardware group. |
| Contingency Plan | Modification of testing strategy to accommodate delay using software simulation. |
| Estimated Resources | 6 additional person-months beginning in July. |
| RE Calculation | P = 0.60. If avg cost/month = $5,000 × 6 months = $30,000. RE = 0.60 × $30,000 = $18,000. |

▶ Risk Record 2: Reusable Component Integration Failure

| Project | Generic commercial web application |
| --- | --- |
| Risk Type | Cost Risk / Performance Risk |
| Priority (1 low … 5 critical) | 4 |
| Risk Factor | Only 70% of the 60 planned reusable software components will successfully integrate into the application. The remaining 30% must be custom-developed. |
| Probability | 80% |
| Impact | 18 additional components must be developed from scratch, adding significant unplanned cost and potentially delaying delivery. |
| Monitoring Approach | Track integration test pass/fail rate per component at each sprint review. Flag any component failing integration after 2 attempts. |
| Contingency Plan | Allocate a dedicated integration team; maintain a buffer of 20 custom development days in the schedule from project start. |
| Estimated Resources | Approx. $25,200 additional development cost (18 × 100 LOC × $14/LOC). |
| RE Calculation | P = 0.80. C = $25,200. RE = 0.80 × $25,200 = $20,160. |

▶ Risk Record 3: Key Staff Turnover

| Project | 12-month enterprise ERP implementation |
| --- | --- |
| Risk Type | Staff / People Risk → Schedule Risk + Cost Risk |
| Priority (1 low … 5 critical) | 3 |
| Risk Factor | Three senior engineers critical to the project architecture may resign mid-project due to competing market opportunities and below-market compensation. |
| Probability | 40% |
| Impact | Loss of key personnel will disrupt project velocity, require expensive recruitment, and increase onboarding time, threatening the delivery milestone. |
| Monitoring Approach | Monthly satisfaction surveys; track retention signals (LinkedIn activity, declining participation). HR to conduct quarterly check-ins. |
| Contingency Plan | Cross-train a junior engineer on each critical system area; document architecture decisions continuously; maintain recruiter relationship for rapid replacement. |
| Estimated Resources | $20,000 per replacement (recruitment + onboarding). Expected avg 1.5 staff lost if risk occurs → $30,000 contingency budget. |
| RE Calculation | P = 0.40. C = $30,000. RE = 0.40 × $30,000 = $12,000. |

▶ Risk Record 4: Requirements Instability

| Project | Custom e-government citizen portal |
| --- | --- |
| Risk Type | Customer Characteristics Risk → Schedule + Cost Risk |
| Priority (1 low … 5 critical) | 5 |
| Risk Factor | The government client has a history of frequent scope changes and lacks a single accountable decision-maker. Requirements may change significantly after the design phase is complete. |
| Probability | 70% |
| Impact | Major rework after design phase — estimated 3 significant change cycles, each requiring redesign of multiple modules and re-approval of test plans. |
| Monitoring Approach | Track number of change requests per sprint. If >2 requests in any sprint, escalate to steering committee. Maintain requirements traceability matrix. |
| Contingency Plan | Implement formal Change Control Board (CCB). Freeze requirements with client sign-off after design review. Any post-freeze change billed as a separate work order. |
| Estimated Resources | $8,000 rework cost per major change × 3 expected changes = $24,000 contingency reserve. |
| RE Calculation | P = 0.70. C = $24,000. RE = 0.70 × $24,000 = $16,800. |

▶ Blank Risk Record Template (for Practice / Exams)

| Project |  |
| --- | --- |
| Risk Type |  |
| Priority (1 low … 5 critical) |  |
| Risk Factor |  |
| Probability |  |
| Impact |  |
| Monitoring Approach |  |
| Contingency Plan |  |
| Estimated Resources |  |
| RE Calculation | RE = P × C = × = |

SECTION 9: QUICK REVISION SUMMARY

⚡ EXAM ESSENTIALS — Memorise These • RE = P × C (Risk Exposure = Probability × Cost) • 4 Risk Components: Performance, Cost, Support, Schedule • 7 Risk Categories: Size, Business, Customer, Process, Environment, Technology, Staff • 7 Principles: Global view, Forward view, Open comms, Integrate, Continuous, Shared vision, Teamwork • MMM = Mitigation + Monitoring + Management