SOFTWARE PROJECT ESTIMATION

Complete Study Guide with Colour-Coded Scenario Calculations

COLOUR LEGEND:

| Main Topics | Sub-topics | Formulas | Calculations | Definitions | Exam Tips |
| --- | --- | --- | --- | --- | --- |

SECTION 1 — FUNDAMENTALS OF SOFTWARE ESTIMATION

1.1  What is Software Project Estimation?

Project Estimation: The process of predicting the cost, effort, schedule and resources required to build a software system before development begins.

▸  Estimates are made to discover the cost of producing a software system.

▸  There is NOT a simple relationship between development cost and the price charged to customers.

▸  Two primary approaches: LOC (Lines of Code) and FP (Functional Point) estimation.

1.2  Software Cost Components

▸  Hardware & software costs

▸  Travel & training costs

▸  Effort costs — salaries of engineers + social/insurance costs

▸  Overheads — networking, communications costs

1.3  Software Productivity

Software Productivity: The rate at which developers produce software and associated documentation. Measured as functionality (LOC or FP) produced per unit time.

▸  QA (Quality Assurance) is NOT counted in software productivity.

▸  Two measurement approaches: Size-related (LOC) and Functionality-related (FP).

⚡ EXAM TIP: Software productivity metric = LOC/pm or FP/pm — know which is language-dependent (LOC) vs language-independent (FP).

SECTION 2 — LINES OF CODE (LOC) ESTIMATION

2.1  LOC Estimation — Core Concepts

▸  Count every line of source code EXCEPT blanks and comments.

▸  Count each declaration, logic statement, and computation statement.

Advantage: Easy to count and calculate.

Disadvantage: Highly dependent on programming language — verbose languages produce more LOC for same functionality.

2.2  PERT Formula for LOC Estimation

When estimating an individual component with historical data, use the weighted 3-point (PERT) formula:

Expected LOC = (S_optimistic + 4 × S_most_likely + S_pessimistic) / 6

S_optimistic: Best-case scenario LOC (everything goes perfectly)

S_most_likely: Most realistic LOC estimate based on experience

S_pessimistic: Worst-case scenario LOC (all challenges occur)

2.3  Full LOC Estimation Workflow

Step 1: Decompose the project into individual functions/features.

Step 2: For each function, gather optimistic, most likely, and pessimistic LOC from past data.

Step 3: Compute Expected LOC for each function using the PERT formula.

Step 4: Sum all Expected LOCs → Total LOC.

Step 5: Derive effort: Effort (pm) = Total LOC ÷ Organisation's LOC/pm rate.

Step 6: Derive cost: Cost = Total LOC × Cost-per-LOC   OR   Cost = Effort × Monthly salary.

2.4  Key Formulas Summary

Cost per LOC = Monthly salary ÷ LOC per person-month

Effort (pm) = Total LOC ÷ LOC per person-month

Project Cost = Total LOC × Cost per LOC

📘  LOC SCENARIO 1 — Mechanical CAD Software

Problem Statement: A mechanical CAD system accepts 2D/3D geometric data from engineers. Estimate total LOC and project cost using historical data. Historical rate: Organisation writes 620 LOC/pm; personnel cost = $8,000/month.

▶ STEP 1 — Estimate LOC per Component (PERT Formula)

Each component's Expected LOC = (Optimistic + 4 × Most Likely + Pessimistic) / 6

Example — 3D Geometric Analysis:

Given: Optimistic = 4,600 | Most Likely = 6,900 | Pessimistic = 8,600

Apply: Expected LOC = (4,600 + 4×6,900 + 8,600) / 6

= (4,600 + 27,600 + 8,600) / 6 = 40,800 / 6

Result: Expected LOC = 6,800 ✓

▶ STEP 2 — Component Summary Table

| Function / Component | Optimistic | Most Likely | Pessimistic | Expected LOC |
| --- | --- | --- | --- | --- |
| 2D geometric analysis | 4100 | 5300 | 6800 | 5300 |
| 3D geometric analysis | 4600 | 6900 | 8600 | 6800 |
| UI and control facilities | 2000 | 2300 | 2600 | 2300 |
| Database management | 2800 | 3350 | 3600 | 3350 |
| Design analysis modules | 7500 | 8400 | 9500 | 8400 |
| Computer graphics display | 4000 | 4950 | 6000 | 4950 |
| Peripheral control | 1500 | 2100 | 2600 | 2100 |
| TOTAL LOC |  |  |  | 33,200 LOC |

▶ STEP 3 — Calculate Effort

Historical rate: Organisation writes 620 LOC per person-month

Total LOC: 5,300 + 6,800 + 2,300 + 3,350 + 8,400 + 4,950 + 2,100 = 33,200 LOC

Effort = 33,200 ÷ 620 ≈ 53 person-months

▶ STEP 4 — Calculate Project Cost

Monthly salary: $8,000/month

Cost per LOC: $8,000 ÷ 620 = $12.9 ≈ $13 per LOC

Project Cost = 33,200 LOC × $13 = $431,600

⚡ EXAM TIP: CAD Example Final Answers: Total LOC = 33,200 | Effort ≈ 53 person-months | Cost = $431,600

📘  LOC SCENARIO 2 — Travel/Booking Application

Problem Statement: A travel application has 5 known modules. Using historical data: Average LOC = 600 LOC/pm, Average cost = $8,000/month. Find total LOC, effort, and project cost.

▶ STEP 1 — Module LOC Table

| Module Name | LOC |
| --- | --- |
| Login & Registration module | 1,000 |
| Search & Booking module | 3,000 |
| Payment & Checkout module | 2,000 |
| User Profile module | 1,500 |
| Feedback & Rating module | 500 |
| TOTAL | 8,000 LOC |

▶ STEP 2 — Calculate Cost per LOC

Given: Monthly rate = $8,000/month | Productivity = 600 LOC/pm

Cost per LOC = $8,000 ÷ 600 = $13.33 per LOC

▶ STEP 3 — Calculate Total Effort

Total LOC: 1,000 + 3,000 + 2,000 + 1,500 + 500 = 8,000 LOC

Effort = 8,000 ÷ 600 = 13.33 person-months

▶ STEP 4 — Calculate Total Project Cost

Project Cost = 8,000 LOC × $13.33 = $106,640

⚡ EXAM TIP: Travel App Final Answers: Total LOC = 8,000 | Effort = 13.33 pm | Cost = $106,640

SECTION 3 — FUNCTIONAL POINT (FP) ESTIMATION

3.1  FP Estimation — Core Concepts

Functional Points (FP): A language-independent metric that measures software from a user's perspective — counting what enters, exits, or is retrieved from the system.

▸  NOT dependent on programming language (unlike LOC).

▸  Measures functionality from the user's point of view.

▸  Weights reflect importance and complexity of operations.

3.2  The Five FP Components

External Inputs (EI): Functions related to data ENTERING the system (e.g. forms, logins, uploads).

External Outputs (EO): Functions related to data EXITING the system (e.g. reports, messages, downloads).

External Enquiries (EQ): Queries that RETRIEVE data without changing the system (read-only lookups).

Internal Logic Files (ILF): User-identifiable groups of logically related data MAINTAINED INSIDE the application boundary (NOT log files).

External Interface Files (EIF): Logical files of OTHER applications that YOUR system uses/reads.

3.3  Standard FP Weighting Table

| Measurement Parameter | Low (Simple) | Average | High (Complex) |
| --- | --- | --- | --- |
| External Inputs (EI) | 3 | 4 | 6 |
| External Outputs (EO) | 4 | 5 | 7 |
| External Enquiries (EQ) | 3 | 4 | 6 |
| Internal Logic Files (ILF) | 7 | 10 | 15 |
| External Interface Files (EIF) | 5 | 7 | 10 |

⚡ EXAM TIP: Memorise ILF weights: 7 / 10 / 15 — these are the highest weights and most commonly tested. EIF is 5 / 7 / 10.

3.4  FP Calculation Formulas

UFP = Σ (Count of each type × Weight for its complexity)

CAF = 0.65 + (0.01 × ΣFi)    where ΣFi = sum of 14 VAF answers

FP = UFP × CAF

Effort = FP ÷ Productivity (FP per person-week or per person-month)

Duration = Effort ÷ Team Size

3.5  The 14 Value Adjustment Factor (VAF) Questions

Each question is answered on a scale of 0–5: 0=not important, 1=incidental, 2=moderate, 3=average, 4=significant, 5=essential.

| # | Value Adjustment Factor (VAF) Question — Scale: 0 (not important) to 5 (essential) |
| --- | --- |
| 1 | Does the system require reliable backup and recovery? |
| 2 | Are specialized data communications required? |
| 3 | Are there distributed processing functions? |
| 4 | Is performance critical? |
| 5 | Will the system run in a heavily utilized operational environment? |
| 6 | Does the system require online data entry? |
| 7 | Does online data entry require multi-screen/operations input? |
| 8 | Are the Internal Logic Files updated online? |
| 9 | Are the inputs, outputs, files, or inquiries complex? |
| 10 | Is the internal processing complex? |
| 11 | Is the code designed to be reusable? |
| 12 | Are conversion and installation included in the design? |
| 13 | Is the system designed for multiple installations in different organizations? |
| 14 | Is the application designed to facilitate change and ease of use by the user? |

⚡ EXAM TIP: CAF range: Min = 0.65+(0.01×0×14) = 0.65 | Max = 0.65+(0.01×5×14) = 1.35 — FP can vary by ±35% around UFP.

📗  FP SCENARIO 1 — SafeHome Security System

Problem Statement: The SafeHome user-interaction subsystem handles external inputs (password, panic button, activate/deactivate), external outputs (messages, sensor status), external inquiries (zone inquiry, sensor inquiry), 1 internal file (system configuration), and 4 external interface files (test sensor, zone setting, activate/deactivate, alarm alert). All functions are LOW complexity. System is moderately complex (all 14 VAF answers = 2). Find FP.

▶ STEP 1 — Identify and Count FP Components

▸  External Inputs (EI): password, panic button, activate/deactivate → Count = 3

▸  External Outputs (EO): messages, sensor status → Count = 2

▸  External Enquiries (EQ): zone inquiry, sensor inquiry → Count = 2

▸  Internal Logic Files (ILF): system configuration file → Count = 1

▸  External Interface Files (EIF): test sensor, zone setting, activate/deactivate, alarm alert → Count = 4

▶ STEP 2 — UFP Calculation Table (Low complexity for all)

| Parameter | Count | Weight | Complexity | Count × Weight |
| --- | --- | --- | --- | --- |
| External Inputs (EI) | 3 | 3 | Low | 3×3 = 9 |
| External Outputs (EO) | 2 | 4 | Low | 2×4 = 8 |
| External Enquiries (EQ) | 2 | 3 | Low | 2×3 = 6 |
| Internal Logic Files (ILF) | 1 | 7 | Low | 1×7 = 7 |
| External Interface Files (EIF) | 4 | 5 | Low | 4×5 = 20 |
| TOTAL UFP |  |  |  | UFP = 9+8+6+7+20 = 50 |

UFP = 9 + 8 + 6 + 7 + 20 = 50

▶ STEP 3 — Calculate CAF

Complexity: Moderate — all 14 VAF questions answered = 2

ΣFi = 14 × 2 = 28

CAF = 0.65 + (0.01 × 28) = 0.65 + 0.28 = 0.93

▶ STEP 4 — Calculate Final FP

FP = UFP × CAF = 50 × 0.93 = 46.5 FP

▶ STEP 5 — Derive Effort & Duration (if productivity given)

If team productivity = 60 FP/person-week and team size = 5:

Effort = 46.5 ÷ 60 = 0.775 person-weeks

Duration = 0.775 ÷ 5 = 0.155 weeks  (≈ 1 day)

⚡ EXAM TIP: SafeHome Answers: UFP = 50 | CAF = 0.93 | FP = 46.5. All at LOW complexity — weight values used: EI=3, EO=4, EQ=3, ILF=7, EIF=5.

📗  FP SCENARIO 2 — Large-Scale System

Problem Statement: A system has: User Inputs=55, User Outputs=35, User Enquiries=40, Internal Logical Files=8, External Interfaces=5. All FP types are LOW complexity. Product is significantly complex so all 14 VAF questions answered = 4. Calculate FP.

▶ STEP 1 — UFP Calculation Table

| Parameter | Count | Weight | Complexity | Count × Weight |
| --- | --- | --- | --- | --- |
| External Inputs (EI) | 55 | 3 | Low | 55×3 = 165 |
| External Outputs (EO) | 35 | 4 | Low | 35×4 = 140 |
| External Enquiries (EQ) | 40 | 3 | Low | 40×3 = 120 |
| Internal Logic Files (ILF) | 8 | 7 | Low | 8×7 = 56 |
| External Interface Files (EIF) | 5 | 5 | Low | 5×5 = 25 |
| TOTAL UFP |  |  |  | UFP = 165+140+120+56+25 = 506 |

UFP = 165 + 140 + 120 + 56 + 25 = 506

▶ STEP 2 — Calculate CAF

Complexity: Significant — all 14 VAF questions answered = 4

ΣFi = 14 × 4 = 56

CAF = 0.65 + (0.01 × 56) = 0.65 + 0.56 = 1.21

▶ STEP 3 — Calculate Final FP

FP = UFP × CAF = 506 × 1.21 = 612.26 FP

⚡ EXAM TIP: Key contrast: Ex1 CAF=0.93 (moderate) REDUCES FP below UFP. Ex2 CAF=1.21 (significant) INCREASES FP above UFP. CAF < 1 means system is simple; CAF > 1 means complex.

SECTION 4 — LOC vs FP COMPARISON & EXAM READY SUMMARY

4.1  LOC vs FP — Side-by-Side Comparison

| Aspect | LOC Estimation | FP Estimation |
| --- | --- | --- |
| Basis | Source lines of code | User-visible functionality |
| Language dep. | Yes — varies by language | No — language independent |
| Measurement | Count non-blank, non-comment lines | Count EI, EO, EQ, ILF, EIF |
| Formula | Expected = (O + 4M + P) / 6 | FP = UFP × CAF |
| Effort | Effort = LOC / LOC per pm | Effort = FP / Productivity |
| Cost | Cost = LOC × ($/LOC) | Cost = FP × ($/FP) |
| Best for | Developer-oriented estimation | Client-oriented estimation |
| Weakness | Penalizes verbose languages | Subjective counting rules |

4.2  All Formulas at a Glance

LOC PERT:   Expected LOC = (O + 4M + P) / 6

LOC Effort: Effort (pm) = Total LOC ÷ LOC per person-month

LOC Cost:   Cost = Total LOC × (Monthly salary ÷ LOC/pm)

FP UFP:     UFP = Σ (Count × Weight) for each of 5 types

FP CAF:     CAF = 0.65 + (0.01 × ΣFi)   [ΣFi = sum of 14 answers, 0–5 each]

FP Final:   FP = UFP × CAF

FP Effort:  Effort = FP ÷ Productivity

Duration:   Project Duration = Effort ÷ Team Size

4.3  Common Exam Scenarios & Quick Solutions

⚡ EXAM TIP: If asked 'find cost' with LOC: (1) Sum LOC across modules → (2) Cost/LOC = salary÷LOC-pm → (3) Total cost = sum×cost/LOC

⚡ EXAM TIP: If asked 'find FP' with complexity table: (1) Fill table with count×weight → (2) Sum = UFP → (3) CAF from 14 Qi → (4) FP = UFP×CAF

⚡ EXAM TIP: If CAF answers are uniform (all = k): ΣFi = 14k → CAF = 0.65 + 0.14k → No need to add 14 numbers individually.

⚡ EXAM TIP: LOC is better for developers estimating implementation effort. FP is better for clients and early-stage planning before coding starts.

⚡ EXAM TIP: Always show your work in steps: Given → Formula → Substitution → Answer. Partial credit is given per step.

Software Project Estimation — Study Guide  |  LOC & FP Methods  |  All Scenarios with Worked Calculations